## Sheet1
Week | Tasks | Effort | Description
2021-11-22 | Create project plan | Low | Create weely plan Create trello board Create Git repo
2021-11-29 | Set up Azure cloud shell | Medium | Create cloud based development environment Create project scaffolding Create requirement.txt file Create python virtual environment Create script file and test file Run local test and make sure everything runs correctly
2021-12-06 | Set up GitHub actions for CI | Medium | Enable Github actions Modify the yml file code Run remote test and verify test pass
2021-12-13 | Complete CD on Azure | High | Replace scaffolding code with Flask ML code Authorize Azure App Service Enable CD with Azure Pipelines Add Azure pipeline yaml config file Enable Github and Azure Pipelines Deploy the project Verify prediction
2021-12-20 | Documentation | Medium | Prepare screenshots Add instructions of all steps into README.md
2021-12-27 | Prepare and submit | Low | Record a video to show all steps Submit the project
Quarterly Goals | Yearly Goals
CI/CD chain start working | Using Docker and Kubernetes
Flask ML app is running | Complete CI/CD chain with quality check
Beta version of application is deployed | Load test is integrated into pipeline